## Team1_Estimated_Effort
|  |  | Role | Owners | Estimated | Effort | Actual | Actual
Task Name: (Dependencies top to bottom) |  |  |  |  | By Task | Subtotals | By Task | Subtotals
Preliminary &
Parallel Tasks | Architecture
|  | Design architecture | Architertural Manager | Andres | 4 | 4 | 3 | 3
Requirements
|  | Gather | Requirements Engineer | Andres | 3 | 3 | 3 | 3
|  | Analyze | Requirements Engineer | Andres | 3 | 3 | 2 | 2
|  | Specify | Requirements Engineer | Andres | 3 | 3 | 3 | 3
Documentation
|  | Release Plan | Project Manager, Developers | Andres, Andrew, Forrest, Kevin | 8 | 8 | 8 | 8
|  | Requirements Document | Project Manager, Requirements Engineer | Andres | 4 | 4 | 4 | 4
|  | Project Plan | Project Manager | Kevin | 20 | 12 | 12 | 12
|  | Architecture Document | Architect | Andres
|  | Test Report | Tester | Forrest, Andrew | 1 | 1 | 2 | 2
|  | User Guide & System Admin Doc | Developers, Requirements Engineer | Andres | 4 | 4 | 4 | 4
Coding | Development
Iteration 1: |  | Determine technology needs | Developers | Andres, Andrew, Forrest, Kevin | 1 | 1 | 4 | 4
|  | Research and learn new language and environment | Developer | Andres, Andrew, Forrest, Kevin | 10 | 10 | 20 | 20
|  | Implement classes | Developer | Andrew | 50 | 50 | 60 | 60
|  | Unit Testing | Developer | Forrest, Andrew | 8 | 8 | 7 | 7
Analysis
|  | System Testing | Tester | Forrest, Andrew | 5 | 5 | 7 | 7
|  | Bug fix as required | Tester, Developer | Andres, Andrew, Forrest, Kevin | 3 | 3 | 6 | 6
|  | Evaluate needs for next iteration | Project Manager | Andres, Andrew, Forrest, Kevin | 1 | 1 | 2 | 2
Coding | Design
Iteration 2: |  | Implement any design changes | Project Manager | Andres, Andrew, Forrest, Kevin | 4 | 4 | 6 | 6
|  | Risk analysis | Project Manager | Andres, Andrew, Forrest, Kevin | 1 | 1 | 1 | 1
Development
|  | Review requirements | Developer | Andrew, Kevin | 2 | 2 | 3 | 3
|  | Implement UI | Developer | Andrew, Kevin | 10 | 10 | 20 | 20
|  | Unit Testing | Developer | Forrest, Andrew | 1 | 1 | 1 | 1
Analysis
|  | System Testing | Tester | Forrest | 2 | 2 | 2 | 2
|  | Bug fix as required | Tester, Developer | Andres, Andrew, Forrest, Kevin | 3 | 3 | 5 | 5
|  | Evaluate needs for next iteration | Project Manager | Andres, Andrew, Forrest, Kevin | 1 | 1 | 3 | 3
TOTAL | [7 empty] | 177